## Sheet1
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | Sprint 1 | US-001 | Project Requirement Analysis | MUST HAVE | No Dependency | Rahul, Vijay, Yashas, Sriram, Usha, Sai Kiran | 3 - Completed
S1 | Sprint 2 | US-002 | Finalize Technology Stack (React, Node js, APIs) | MUST HAVE | Research Tech Evaluation | Rahul, Vijay, Yashas, Sriram, Usha, Sai Kiran | 3 - Completed
S1 | Sprint 3 | US-003 | System Architecture Design | MUST HAVE | Architecture Planning | Rahul, Vijay, Yashas, Sriram, Usha, Sai Kiran | 3 - Completed
S1 | Sprint 4 | US-004 | GitHub Repository & Project Structure Setup | MUST HAVE | GitHub | Rahul, Vijay, Yashas, Sriram, Usha, Sai Kiran | 3 - Completed
S2 | Sprint 5 | US-005 | Custom Purpule Theme Implementation | MUST HAVE | Tailwind CSS | Rahul, Usha, Vijay | 3 - Completed
S2 | Sprint 6 | US-006 | Supabase / REST API Layer Integration | MUST HAVE | Supabase | Sriram, Rahul | 3 - Completed
S2 | Sprint 7 | US-007 | PostgreSQL Database Configuration | MUST HAVE | PostgreSQL | Sai Kiran,Usha, Vijay | 3 - Completed
S3 | Sprint 8 | US-008 | Real-time Threat Detection Dashboard | MUST HAVE | React.js, PostgreSQL | Rahul, Sriram, Usha | 3 - Completed
S3 | Sprint 9 | US-009 | Geospatial Attack Map Implementation | MUST HAVE | Leaflet.js Map Visualization | Rahul, Yashas, Usha | 3 - Completed
S3 | Sprint 10 | US-010 | Data Ingestion Pipeline (CSV, JSON, REST) | MUST HAVE | PostgreSQL, REST API | Vijay,Sai Kiran, Sriram | 3 - Completed
S3 | Sprint 11 | US-011 | Gemini Integration for Threat Summarization | MUST HAVE | Gemini-3-flash API | Sai Kiran, Vijay, Yashas | 3 - Completed
S4 | Sprint 12 | US-012 | Nmap Scanner Integration (Quick, Full, SYN, Service Detection) | MUST HAVE | Nmap | Sriram, Rahul | 3 - Completed
S6 | Sprint 13 | US-013 | IP Agent AI Chatbot | MUST HAVE | Gemini API | Sai Kiran, Vijay, Yashas | 3 - Completed
S6 | Sprint 14 | US-014 | Auto-Block Engine for Critical Threats | MUST HAVE | PostgreSQL | Rahul, Usha | 3 - Completed
S6 | Sprint 15 | US-015 | Data Preprocessing Pipeline | MUST HAVE | PostgreSQL | Rahul, Vijay, Yashas, Sriram, Usha, Sai Kiran | 3 - Completed
S6 | Sprint 16 | US-016 | System Architecture Diagram Display | MUST HAVE | React.js | Usha, Vijay | 3 - Completed
S6 | Sprint 17 | US-017 | REST API Endpoints for Threat Data | MUST HAVE | Supabase, REST API | Sriram, Yashas | 3 - Completed
S6 | Sprint 18 | US-018 | Live API Stream Integration | MUST HAVE | REST API, Live Stream | Sai Kiran, Vijay | 3 - Completed
S6 | Sprint 19 | US-019 | Deployment on Lovable.app Cloud Platform | MUST HAVE | Lovable.app | Rahul | 3 - Completed
S6 | Sprint 20 | US-020 | CSV, JSON Data Format Support | MUST HAVE | CSV, JSON | Yashas, Vijay | 3 - Completed
S6 | Sprint 21 | US-021 | Complete Integration Testing | MUST HAVE | Complete System | Rahul, Vijay, Yashas, Sriram, Usha, Sai Kiran | 3 - Completed
| Sprint 22 | US-022 | System testing | MUST HAVE | Complete System | Rahul, Vijay, Yashas, Sriram, Usha, Sai Kiran | 4 - Completed
| Sprint 23 | US-023 | Bug fixing | MUST HAVE | Complete System | Rahul,Usha, Srira, | 5 - Completed
| Sprint 24 | US-024 | Agile Documention | MUST HAVE | Sprint Records | Usha | 6 - Completed